## Sprint Dashboard
INNOVATORS AI HUB — SEO SPRINT & WEBPAGE DEVELOPMENT TRACKER
Day 1 Focus: Core Technical SEO Fixes, 5 Dedicated AI Agent Webpages Setup & Foundational Research
Team Member | Role | Day 1 Tasks | Completed | In Progress | Not Started | Hours Allocated | Status
Aditya Singh | Team Lead (Dev & Tech SEO) | 8 | 5 | 3 | 0 | 5.0 hrs | Active / Ahead of Schedule
Aditya Dubey | Assistant Team Lead (Keyword & PR) | 4 | 0 | 2 | 2 | 5.0 hrs | In Progress
Drishti Chaudhary | Content & Copywriting Specialist | 4 | 0 | 1 | 3 | 5.0 hrs | In Progress
Agrima Agarwal | UI/Visual Asset Designer | 4 | 0 | 1 | 3 | 5.0 hrs | In Progress
Aksh Chauhan | Directory & Citation Specialist | 4 | 0 | 1 | 3 | 5.0 hrs | In Progress
SPRINT HIGHLIGHTS & KEY MILESTONES
Target Canonical Domain | https://www.innovatorsaihub.com/ (with 301 redirect from non-www & /home)
Google Analytics 4 Status | Configured (Measurement ID: G-FRNF7K23EF installed in index.html)
Sitemap & Robots Status | Clean XML sitemap & robots.txt generated at domain root
New Webpages Under Dev | 5 Pages: WhatsApp AI Agent, LinkedIn AI Agent, Gmail AI Agent, Voice Calling AI, SEO AI Agent
Social Media SEO Status | Excluded as per strategic realignment — focus redirected 100% to Search Engines & Webpages
Daily Work Commitment | Each member executes 3h focused deep-work (structured as 5h deliverables)

## Day 1 - Tasks
DAY 1 DETAILED TASK TRACKER — EXECUTION & REAL-TIME UPDATES
Update 'Status', 'Actual Time Spent', and 'Notes / Deliverable Link' daily. Aditya Singh (TL) reviews every evening.
Task ID | Assigned To | Category | Task Name & Detailed Objective | Target Deliverable | Alloc. Time | Actual Time | Status | Completed Date | Proof / Deliverable Link | Daily Notes & Next Steps
AS-01 | Aditya Singh (TL) | Dev Ops | Clone GitHub repo & establish local testing branch | Local repository setup with clean git status | 30 min | 25 min | Completed | 2026-09-17 | Local scratch repo | Repo cloned from Sagaswager/innovatorsaihub
AS-02 | Aditya Singh (TL) | Technical SEO | Fix Canonical URL tag & remove dynamic override script in index.html | Fixed <link rel='canonical' href='https://www.innovatorsaihub.com/'> | 45 min | 35 min | Completed | 2026-09-17 | index.html:L16 | Purged dynamic script that split SEO ranking across /home
AS-03 | Aditya Singh (TL) | Server Config | Configure 301 Permanent Redirects for /home and non-www in vercel.json | Updated vercel.json with host and path 301 redirects | 45 min | 30 min | Completed | 2026-09-17 | vercel.json:L2-24 | Forces all traffic to primary domain https://www.innovatorsaihub.com/
AS-04 | Aditya Singh (TL) | Technical SEO | Update robots.txt and sitemap.xml to primary canonical domain | public/robots.txt and public/sitemap.xml verified | 30 min | 20 min | Completed | 2026-09-17 | public/robots.txt, public/sitemap.xml | Active routes added (/services, /portfolio, /contact, /register, /join)
AS-05 | Aditya Singh (TL) | Analytics | Install active Google Analytics GA4 Measurement ID G-FRNF7K23EF | index.html updated with active gtag snippet | 30 min | 15 min | Completed | 2026-09-18 | index.html:L18-25 | Replaced placeholder G-XXXXXXXXXX with live tracking tag
AS-06 | Aditya Singh (TL) | Webpage Dev | Scaffold routing & component structure for 5 dedicated AI Agent pages | Vite/React routes created for: /whatsapp-ai-agent, /linkedin-ai-agent, /gmail-ai-agent, /voice-calling-ai-agent, /seo-ai-agent | 1 hr 30 min |  | In Progress |  | App.tsx & Sections/ | Building page scaffolding and dynamic title/description support
AS-07 | Aditya Singh (TL) | Technical SEO | Google Search Console domain ownership verification & sitemap submission | Verified property in GSC & submitted sitemap.xml | 45 min |  | In Progress |  | search.google.com | Waiting for DNS TXT record or HTML verification tag
AS-08 | Aditya Singh (TL) | Management | Daily team sync, task tracker review & git commit/push to origin | Consolidated git commit pushed to GitHub main branch | 30 min |  | In Progress |  | GitHub commit log | Syncing daily with team to unblock copy & visual assets
AD-01 | Aditya Dubey (ATL) | Keyword Research | Keyword research for 5 new agent pages (WhatsApp, LinkedIn, Gmail, Voice, SEO) | Master keyword spreadsheet with search volume, intent & target URL | 1 hr 45 min |  | In Progress |  | Shared Sheet / Drive | Targeting high-intent B2B search terms across Indian market
AD-02 | Aditya Dubey (ATL) | Competitor Audit | Competitor landing page audit for AI agent providers in India | Comparative audit sheet: sections, pricing models, CTA formats | 1 hr 15 min |  | In Progress |  | Competitor Doc | Auditing top 3 ranking pages for each of the 5 agent types
AD-03 | Aditya Dubey (ATL) | Link Building Prep | Compile curated list of 15 tech blogs & publications for guest post pitches | Spreadsheet: Domain, DA, Editorial Guidelines, Contact Email | 1 hr 15 min |  | Not Started |  | Outreach Sheet | Finding high-DA sites with relevant AI/SaaS categories
AD-04 | Aditya Dubey (ATL) | Digital PR | Register expert profile on Featured.com, Qwoted & Connectively (HARO) | 3 active source profiles with company bio & website backlink | 45 min |  | Not Started |  | Platform URLs | Ready to respond to journalist queries on enterprise AI automation
DR-01 | Drishti Chaudhary | Content Writing | Draft complete sales & SEO copy for Page 1: WhatsApp AI Agent | Google Doc: H1, subhead, 4 core features, 3 use-cases, pricing, 5 FAQs | 1 hr 45 min |  | In Progress |  | Docs: WhatsApp Agent Copy | Focusing on 24/7 lead qualification, multi-lingual support, CRM sync
DR-02 | Drishti Chaudhary | Content Writing | Draft complete sales & SEO copy for Page 2: LinkedIn AI Agent | Google Doc: H1, subhead, auto-prospecting workflow, safety compliance, FAQs | 1 hr 30 min |  | Not Started |  | Docs: LinkedIn Agent Copy | Highlighting personalized messaging & automated meeting bookings
DR-03 | Drishti Chaudhary | On-Page SEO | Write optimized Meta Titles (<60c) & Descriptions (<160c) for all 5 agent pages | Meta tags copy sheet with primary keyword & high-CTR call to action | 45 min |  | Not Started |  | Meta Tags Doc | Ensuring unique title tags that will rank on Google
DR-04 | Drishti Chaudhary | Branding Copy | Draft Master Company Description in 3 lengths (160c, 300c, 750c) | Standard company bio for directories, Google Business Profile & headers | 1 hr |  | Not Started |  | Company Bio Doc | Embedding keywords naturally into brand narrative
AG-01 | Agrima Agarwal | Design System | Setup Canva Brand Kit (colors, fonts, logo assets from website) | Canva Brand Kit with Dark Zinc (#09090b), Cyan & Indigo accents | 45 min |  | In Progress |  | Canva Folder | Extracting assets from repo to maintain exact website aesthetic
AG-02 | Agrima Agarwal | UI Graphics | Design Hero product UI mockup for WhatsApp AI Agent page | High-res transparent PNG: smartphone chat interface showing AI agent workflow | 1 hr 45 min |  | Not Started |  | Canva / Drive PNG | Clean mock chat demonstrating real-time lead capture
AG-03 | Agrima Agarwal | UI Graphics | Design Hero product UI mockup for LinkedIn AI Agent page | High-res transparent PNG: dashboard card showing connection requests & meetings booked | 1 hr 30 min |  | Not Started |  | Canva / Drive PNG | Illustrating enterprise B2B lead generation
AG-04 | Agrima Agarwal | Local SEO Assets | Create Google Business Profile Cover (1024x576) & 3 service badge graphics | Pack of 4 high-res PNG visual assets ready for Day 3 GBP submission | 1 hr |  | Not Started |  | Drive: GBP Assets | Professional imagery to ensure instant verification trust
AK-01 | Aksh Chauhan | Local SEO Prep | Verify & standardize NAP (Name, Address, Phone) master data sheet | Strict NAP document with zero variance for 12 directory listings | 1 hr |  | In Progress |  | Drive: Master NAP | Name: Innovators AI HUB ¦ Address: Sec 19 Noida ¦ Phone: +91 9810875683
AK-02 | Aksh Chauhan | Directory Research | Audit registration requirements for 12 top Indian & Tech directories | Checklist: Justdial, Sulekha, IndiaMART, YellowPages, Clutch, GoodFirms, G2, Crunchbase | 1 hr 45 min |  | Not Started |  | Directory Matrix Sheet | Noting required OTP methods, categories & review policies
AK-03 | Aksh Chauhan | Profile Links | Checklist & account preparation for 8 profile backlink platforms | Setup guide for GitHub Org, Dev.to, Hashnode, Medium, About.me, Gravatar | 1 hr 15 min |  | Not Started |  | Profile Tracker Sheet | Listing exact fields to include company URL
AK-04 | Aksh Chauhan | AI Aggregators | Research & audit 10 top AI tool directories & aggregator submission guidelines | Curated submission sheet: Futurepedia, Toolify.ai, There's An AI For That, FutureTools, Dang.ai, AI Valley, etc. | 1 hr |  | Not Started |  | AI Aggregators Sheet | High-DA niche backlinks that trigger LLM citations in ChatGPT & Perplexity

## 5 AI Agent Webpages
BLUEPRINT & SPECIFICATIONS FOR 5 NEW DEDICATED AI AGENT WEBPAGES
Dedicated landing pages designed to rank on Google for high-intent search queries in India. Managed & coded by Aditya Singh.
Page # | AI Agent Service | Proposed URL Path | Primary Target Keywords | Core Value Proposition | Copy Lead | Design Lead | Dev & SEO Lead
1 | WhatsApp AI Agent | https://www.innovatorsaihub.com/whatsapp-ai-agent | whatsapp ai agent, whatsapp automation for business india, ai whatsapp bot crm, automated customer support whatsapp | 24/7 intelligent instant replies, automated lead qualification, booking appointments, and native CRM synchronization (HubSpot, Zoho). | Drishti Chaudhary | Agrima Agarwal | Aditya Singh
2 | LinkedIn AI Agent | https://www.innovatorsaihub.com/linkedin-ai-agent | linkedin ai agent, automated linkedin outreach india, b2b linkedin lead generation agent, ai appointment setter linkedin | Hyper-personalized connection outreach, automatic prospect qualification, and direct calendar booking without account bans. | Drishti Chaudhary | Agrima Agarwal | Aditya Singh
3 | Gmail / Email AI Agent | https://www.innovatorsaihub.com/gmail-ai-agent | gmail ai agent, ai email automation business, ai email assistant india, automated inbox management agent | Automated inbox sorting, smart contextual draft generation, follow-up scheduling, and CRM data extraction from inbound inquiries. | Drishti Chaudhary | Agrima Agarwal | Aditya Singh
4 | Voice Calling AI Agent | https://www.innovatorsaihub.com/voice-calling-ai-agent | ai voice calling agent, automated outbound calling agent india, ai voice bot customer support, conversational voice ai india | Human-like outbound and inbound voice calls, instant appointment confirmations, lead qualification over phone, and live call transfer. | Drishti Chaudhary | Agrima Agarwal | Aditya Singh
5 | SEO AI Agent | https://www.innovatorsaihub.com/seo-ai-agent | seo ai agent, autonomous ai seo services india, ai search engine optimization agent, programmatic seo agent | Autonomous keyword rank tracking, continuous programmatic on-page optimization, content gap identification, and backlink opportunity discovery. | Drishti Chaudhary | Agrima Agarwal | Aditya Singh

## Daily Standup Log
DAILY STANDUP & MANAGER UPDATE LOG
Date | Team Member | Key Accomplishments Today | Blockers / Impediments | Next Day Priority | Hours Reported | TL Sign-Off
2026-09-17 | Aditya Singh | Fixed canonical tags, 301 redirects in vercel.json, updated robots.txt and sitemap.xml | None | Integrate GA4 tag and start 5 AI agent page routing | 5.0 hrs | VERIFIED
2026-09-18 | Aditya Singh | Installed live GA4 measurement tag (G-FRNF7K23EF), structured Day 1 tasks & 5 webpage blueprints | Awaiting Google verification DNS entry | Scaffold /whatsapp-ai-agent & /linkedin-ai-agent UI templates | 5.0 hrs | VERIFIED
2026-09-18 | Aditya Dubey | Completed initial keyword search volume pull for WhatsApp and Voice Calling agents | Ubersuggest daily search limit reached (switched to GKP) | Finalize keyword sheets for remaining 3 agents | 5.0 hrs | PENDING
2026-09-18 | Drishti Chaudhary | Drafted outline and core features for WhatsApp AI Agent landing page | Need confirmation on exact starting pricing plans | Write complete WhatsApp copy and start LinkedIn page | 5.0 hrs | PENDING
2026-09-18 | Agrima Agarwal | Extracted website color palette and established Canva UI design system | None | Finish WhatsApp smartphone mockup visual asset | 5.0 hrs | PENDING
2026-09-18 | Aksh Chauhan | Compiled Master NAP document and audited Justdial & IndiaMART requirements | Phone OTP coordination needed with TL | Prepare documentation for remaining 10 directories | 5.0 hrs | PENDING